## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.
REVISAR EL NÚMERO DE ENTREGAS ESTE CURSO!!!!!
La columna estatus es redundante con Execution Period. Poner autocalculada.
Poner filtros en las columnas.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 3666.25
|  | Actual: | 361.25
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 1 | Manager | Make plans |  | 2026-02-03 08:30 | 2026-02-03 10:30 | Completed | 2 | 1.5 | 100 | 75 | Realizar reparto de tareas para el requisito 0
2 | T0002/M | Management | Student 2 | Analyst | Write report |  | 2026-02-14 15:30 | 2026-02-14 19:30 | Completed | 3 | 4 | 120 | 160 | Realizar Chartening Report
3 | T0003/M | Management | Student 3 | Manager | Initialise repository |  | 2026-02-05 18:30 | 2026-02-05 18:45 | Completed | 0.25 | 0.25 | 12.5 | 12.5 | Instanciar repositorio de GitHub
4 | T0004/M | Management | ALL | Other | Other (Describe) |  | 2026-02-16 10:30 |  |  | 0.5 | 0.5 | 5 | 5 | Rellenar el Identification Form
5 | T0005/D | Development | Student 3 | Developer | Create dev. config. |  | 2026-02-05 19:00 | 2026-02-05 19:30 | Completed | 0.25 | 0.5 | 6.25 | 12.5 | Instanciar el proyecto Hello-World como Acme-Starters-C
6 | T0006/D | Development | Student 5 | Developer | Customise the starter |  | 2026-02-06 10:30 | 2026-02-06 12:30 | Completed | 3 | 2 | 75 | 50 | Personalizar proyecto base acorde a las diapositivas S03
7 | T0007/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-06 21:00 | 2026-02-06 21:15 | Completed | 0.5 | 0.25 | 12.5 | 6.25 | Añadir Constraints del modelo CG
8 | T0008/R/T0005/D | Revision | Student 4 | Tester | Check task | T0005/D | 2026-02-07 10:00 | 2026-02-07 10:30 | Completed | 1 | 0.5 | 30 | 15 | Revisar tarea
9 | T0009/M | Management | Student 1 | Manager | Make plans |  | 2026-02-08 21:30 | 2026-02-08 22:00 | Completed | 0.5 | 0.5 | 25 | 25 | Repartición de requisitos del nivel C
10 | T0010/D | Development | Student 1 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S1/1 (Implementación del modelo Model C01)
11 | T0011/D | Development | Student 2 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S2/1 (Implementación del modelo Model C02)
12 | T0012/D | Development | Student 3 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S3/1 (Implementación del modelo Model C03)
13 | T0013/D | Development | Student 4 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S4/1 (Implementación del modelo Model C04)
14 | T0014/D | Development | Student 5 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S5/1 (Implementación del modelo Model C05)
15 | T0015/M | Management | Student 4 | Operator | Prepare dep. platf. |  |  |  |  | 1 |  | 30 |  | Actualización del framework a la versión 26.2
16 | T0016/D | Development | Student 1 | Developer | Implement feature |  |  |  |  | 5 |  | 125 |  | Realización del requisito S1/2
17 | T0017/D | Development | Student 2 | Developer | Implement feature |  |  |  |  | 5 |  | 125 |  | Realización del requisito S2/2
18 | T0018/D | Development | Student 3 | Developer | Implement feature |  |  |  |  | 5 |  | 125 |  | Realización del requisito S3/2
19 | T0019/D | Development | Student 4 | Developer | Implement feature |  |  |  |  | 5 |  | 125 |  | Realización del requisito S4/2
20 | T0020/D | Development | Student 5 | Developer | Implement feature |  |  |  |  | 5 |  | 125 |  | Realización del requisito S5/2
21 | T0021/D | Development | Student 1 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S1/3
22 | T0022/D | Development | Student 2 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S2/3
23 | T0023/D | Development | Student 3 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S3/3
24 | T0024/D | Development | Student 4 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S4/3
25 | T0025/D | Development | Student 5 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S5/3
26 | T0026/D | Development | Student 1 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S1/4
27 | T0027/D | Development | Student 2 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S2/4
28 | T0028/D | Development | Student 3 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S3/4
29 | T0029/D | Development | Student 4 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S4/4
30 | T0030/D | Development | Student 5 | Developer | Implement feature |  |  |  |  | 8 |  | 200 |  | Realización del requisito S5/4
31 | T0031/D | Development | Student 1 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S1/5
32 | T0032/D | Development | Student 2 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S2/5
33 | T0033/D | Development | Student 3 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S3/5
34 | T0034/D | Development | Student 4 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S4/5
35 | T0035/D | Development | Student 5 | Developer | Implement feature |  |  |  |  | 2 |  | 50 |  | Realización del requisito S5/5
36 | T0036/D | Development | Student 1 | Developer | Implement feature |  |  |  |  | 1 |  | 25 |  | Realización del requisito S1/6
37 | T0037/D | Development | Student 2 | Developer | Implement feature |  |  |  |  | 1 |  | 25 |  | Realización del requisito S2/6
38 | T0038/D | Development | Student 3 | Developer | Implement feature |  |  |  |  | 1 |  | 25 |  | Realización del requisito S3/6
39 | T0039/D | Development | Student 4 | Developer | Implement feature |  |  |  |  | 1 |  | 25 |  | Realización del requisito S4/6
40 | T0040/D | Development | Student 5 | Developer | Implement feature |  |  |  |  | 1 |  | 25 |  | Realización del requisito S5/6
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O